## Sheet1
Capital Improvement Plan
Project | Responsible Party | Time | Total $ | $ Ft. Getty | $ Harbor | $Town Infrastructure | 2005 | 2006 | 2007 | 2008 | 2009
Land Use Planner/Consultant | Town Council & Planning | 2005 | 30 | 30 |  |  | 30
-Landscape Plan & Implementation | Planner | 2006-09 | 140 | 140 |  |  |  | 35 | 35 | 35 | 35
-Parking Plan: Cars, Trailers & Boats | Rec/ Harbor | 2006-08 | 30* | 15 |  | 15 |  | 10 | 10 | 10
-Historical Fortification Plan | Planner & Historical Society | 2006-07 | 10 | 10 |  |  |  | 10
-Potential Uses - 5acre site south of gate house | Recreation | 2005-06 | 12 | 12 |  |  |  | 12
Upgrades to Existing Ft. Getty Activities
-Implement Full Day Summer Camp | Recreation | 2005
-Improve Trails & Picnic Areas | Recreation | 2005-06 | 5 | 5 |  |  | 1 | 1 | 1 | 1 | 1
-Upgrade Existing Restrooms | Recreation | 2006-08 | 35 | 25 |  | 10 |  | 15 | 10 | 10
-Repair Access Road | Town | 2006-07
-Upgrade Electrical Service-Camp Sites | Recreation | 2006-09 | 40 | 40 |  |  |  | 10 | 10 | 10 | 10
Harbor Management Plans
-Install Touch & Go Floats & Dinghy Dock | Harbor | 2005 | 33 |  | 33 |  | 33
-Repair Existing Pier | Harbor | 2005-07 | 45 |  |  | 45 | 13 | 32
-Upgrade Existing Boat Ramp | Harbor | 2006-08 | 50 |  | 25 | 25 |  |  | 25 | 25
-Install New Pump-out Facilities | Rec/Harbor | 2007-08 | 50? | 25 | 25 |  |  |  | 25 | 25
-Develop Plan for Sailing Program- Consultant | Planner | 2005 | 15 |  |  | 15 | 15
-Implement Sailing Program | Rec/Harbor | 2006-09 | 200**
New Costruction Projects |  |  | Total $ K | $K Ft. Getty | $K Harbor | $K Town Infrastructure | 2005 | 2006 | 2007 | 2008 | 2009
-Design Competition Old & New Pavillion | Planner | 2005 | 5 |  |  |  | 5
-Design & Construct Upgrade - Old Pavillion | Planner/ Recreation | 2006-07 | 75 |  |  |  |  | 25 | 50
-Design & Construct New Pavillion | Planner/ Recreation | 2007-09 | 175 | [5 empty] | 25 | 75 | 75
-Construct New Rest Rooms | Recreation | 2007-09 | 25 | [5 empty] | 25
-Feasibility Study New Recreation Facility | Planner | 2008 | 25 | [6 empty] | 25
*Town Labor | Total |  | 1000 | 607 | 83 | 110 | 97 | 160 | 211 | 211 | 121
**Capital Fund Raiser - Sailing Program
| Ft. Getty Fund |  |  | 607 |  |  | 36 | 118 | 166 | 166 | 121
| Harbor Funds |  |  |  | 83 | 110 | 61 | 42 | 45 | 45
** | Sailing Fund Raiser |  | 200